## Resource Sheet
300000
Resource Sheet
Resource Name | Monthly Cost | Estimated Months | Estimated Hours | Hourly Rate (PKR) | Total Cost (PKR)
Project Manager | 50000 | 6 | 96 hrs | 3,125/hr | 300000
UI/UX Designer | 30000 | 6 | 72 hrs | 2,500/hr | 180000
Frontend Developer | 100000 | 4 | 128 hrs | 3,125/hr | 400000
Backend Developer | 120000 | 4 (july–sep + nov) | 132 hrs | 3,635/hr | 480000
Database Administrator | 55000 | 3 | 84 hrs | 1,965/hr | 165000
QA Tester | 60000 | 4 | 120 hrs | 2,000/hr | 240000
DevOps Engineer | 50000 | 3 | 72 hrs | 2,083/hr | 150000
Trainer/Support Officer | 30000 | 2 | 16 hrs | 3750/hr | 60000
Software Deployment | 20000 | 6 (fixed/monthly) | — | — | 120000
Cloud Hosting | 60000 | 1 (Nov only) | — | — | 60000
Reserves (20%) | — | — | — | — | 316000
DBA Overhead (30%) | — | — | — | — | 33000

## Cost Sheet
Cost Sheet (PKR)
Role | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2026-11-01 | 2026-12-01 | Total Cost
Project Manager | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 300000
UI/UX Designer | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 180000
Frontend Developer | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 400000
Backend Developer | 120000 | 120000 | 120000 | 0 | 0 | 120000 | 480000
Database Administrator | 55000 | 55000 | 55000 | 0 | 0 | 0 | 165000
QA Tester | 60000 | 0 | 0 | 60000 | 60000 | 60000 | 240000
DevOps Engineer | 50000 | 0 | 0 | 0 | 50000 | 50000 | 150000
Trainer/Support Officer | 30000 | 0 | 0 | 0 | 0 | 30000 | 60000
Software Deployment | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 120000
Cloud Hosting Service | 60000 | 0 | 0 | 0 | 0 | 0 | 60000
20% of All Estimate | — | 75000 | 75000 | 52000 | 42000 | 72000 | 316000
30% of DBA (Overhead) | — | 16500 | 16500 | 0 | 0 | 0 | 33000
Total/Month | — | 466500 | 466500 | 312000 | 252000 | 432000 | 2504000
Note: It’s 85–90% aligned with your plan structure and task durations, but not 100% accurate in monthly cost distribution per resource because we didn't break down hours day-by-day.